## Sheet1
Requirement ID | Description of Requirement | Story Points | Priority | Sprint No.
1 | User Interface menu | 8 | 1 | 1
2 | First person move controller | 8 | 1 | 1
3 | First person FOV controller | 8 | 1 | 1
4 | First person sound effect | 3 | 1 | 1
5 | Design base map models | 5 | 2 | 2
6 | Design building models | 5 | 2 | 2
7 | Design enemy models | 5 | 2 | 2
8 | Design weapon models | 5 | 2 | 2
9 | HP script | 3 | 3 | 3
10 | Collision for enemy/characters | 1 | 3 | 3
11 | Weapon/bullet collision feedback | 3 | 3 | 3
12 | First person animation controller | 3 | 3 | 3
13 | Enemy animation controller | 3 | 3 | 3
14 | First person UI/UX | 5 | 4 | 4
15 | Interactive characters | 3 | 4 | 4
16 | Interactive items on map | 8 | 4 | 4
17 | Interactive map model | 8 | 4 | 4
18 | Dialogue bubbles | 2 | 4 | 4
19 | BGM for game | 1 | 5 | 5
20 | Sound effect | 2 | 5 | 5
21 | Game Features(i.e. double jump) | 5 | 5 | 5
22 | Story design | 2 | 5 | 5
23 | Particle effects | 5 | 6 | 6
24 | Shadow rendering | 5 | 6 | 6
25 | Game Process Optimization | 3 | 7 | 7
26 | Algorithm optimization | 13 | 7 | 7
27 | Improved performance | 13 | 7 | 7